## Full Start Up Check List
[6 empty] | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21
PROJECT SHEDULE : SAMPLE CLIENT | Due Date | Lead | Support | Vendor support |  | 2021-02-08: In Process; 2021-02-22: Complete (or not doing)
PHASE 1: Develop Concept of Entity | bar: 2021-02-08 to 2021-03-15
Business Plan | bar: 2021-02-08 to 2021-03-15
Concept/Vision | Ccomplete | S and D | Team | bar: 2021-02-08
Case for success | Ccomplete | AEC | AEC | bar: 2021-02-08
Location | Ccomplete | S and D | S and D | bar: 2021-02-08
Competition | Ccomplete | AEC | AEC | Geoff/Mike | bar: 2021-02-08
Programming | Ccomplete | AEC | AEC | bar: 2021-02-08
Staffing | Ccomplete | AEC | AEC | bar: 2021-02-08 to 2021-03-15
Pricing | Ccomplete | TEAM | TEAM | bar: 2021-02-08
Marketing |  | AEC | AEC | bar: 2021-02-08 to 2021-03-15
Financial Projections | bar: 2021-02-08 to 2021-03-15
Staffing Model & Compensation Model | Complete | AEC | AEC | bar: 2021-02-08
Membership Options and pricing | Complete | AEC | AEC | bar: 2021-02-08
Ancillary revenue and expenses | Complete | AEC | AEC | bar: 2021-02-08
Projected costs associated with build out | Complete | AEC | AEC | bar: 2021-02-08
Updated industry benchmarks | Complete | AEC | AEC | bar: 2021-02-08
Feasibility and Opportunity | bar: 2021-02-08 to 2021-03-15
Location selection | Complete | AEC | AEC | bar: 2021-02-08
Feasibility Study | Complete | AEC | AEC | bar: 2021-02-08
Competition Study | Complete | AEC | AEC | bar: 2021-02-08
Basic overview of market opportunities | Complete | AEC | AEC | bar: 2021-02-08
Legally Establish Company and Partnership | bar: 2021-02-08 to 2021-03-15
Set up Legal Structure of company i.e. S. Corp, LLC, Sole Proprietorship etc |  |  | Client | bar: 2021-02-08
Get tax ID number |  |  | Client | bar: 2021-02-08
Register for state and federal taxes |  |  | Client | bar: 2021-02-08
Research required fed,state, local licences and permits |  |  | Client | bar: 2021-02-08
Get a bond to cover customer losses if required in state |  |  | Client | bar: 2021-02-08
Funding-Banking, Company and Partnership legally established, insurance | bar: 2021-02-08 to 2021-03-15
Debt financing |  |  | Client | D/S | bar: 2021-02-08
Equity financing |  |  | Client | D/S | bar: 2021-02-08
Set up bank account(s) |  |  | Client | D/S | bar: 2021-02-08
Acquire needed licences to build and operate |  |  | Client | D/S | bar: 2021-02-08
Negotiate and sign lease |  |  | Client | D/S | bar: 2021-02-08
Get insurance (some for build out period, other insurance kicks in when open) |  |  | Client | D/S | bar: 2021-02-08
PHASE 2: DESIGN & BUILD-OUT | bar: 2021-02-08 to 2021-03-15
Design space | bar: 2021-02-08 to 2021-03-15
Select architect | CUOCO | CUOCO | CUOCO | bar: 2021-02-08 to 2021-02-15
Develop architectural plans | CUOCO | CUOCO | CUOCO | bar: 2021-02-08 to 2021-02-15
Get renderings of clubs for pre-marketing | CUOCO | CUOCO | CUOCO | bar: 2021-02-08 to 2021-03-15
Build Out Space | bar: 2021-02-08 to 2021-03-15
Select contractor |  | Client | Client | bar: 2021-02-08 to 2021-02-15
Obtain construction permits |  | Client | Client | bar: 2021-02-08 to 2021-03-15
Build-out space |  | Client | Client | bar: 2021-02-08 to 2021-03-15
Order and Receive Equipment & Furnishings (buy/lease) | bar: 2021-02-08 to 2021-03-15
Cardio |  | AEC | AEC | AEC |  | 2021-02-08: AEC; 2021-02-15: AEC; 2021-02-22: AEC; 2021-03-01: AEC
Strength training |  | AEC | AEC | AEC |  | 2021-02-08: AEC; 2021-02-15: AEC; 2021-02-22: AEC; 2021-03-01: AEC
Functional training |  | AEC | AEC | AEC |  | 2021-02-08: AEC; 2021-02-15: AEC; 2021-02-22: AEC; 2021-03-01: AEC
AV - Sound systems - wiring and wireless |  | AEC | AEC | AEC |  | 2021-02-08: AEC; 2021-02-15: AEC; 2021-02-22: AEC; 2021-03-01: AEC
Office desks chairs |  | AEC | AEC | AEC |  | 2021-02-08: AEC; 2021-02-15: AEC; 2021-02-22: AEC; 2021-03-01: AEC
Lobby furnature |  | AEC | AEC | AEC |  | 2021-02-08: AEC; 2021-02-15: AEC; 2021-02-22: AEC; 2021-03-01: AEC
Lockers and benches/chairs |  | AEC | AEC | AEC |  | 2021-02-08: AEC; 2021-02-15: AEC; 2021-02-22: AEC; 2021-03-01: AEC
Other |  | AEC | AEC | AEC |  | 2021-02-08: AEC; 2021-02-15: AEC; 2021-02-22: AEC; 2021-03-01: AEC
PHASE 3: PRE-OPENING & FIRST MONTHS OF OPERATIONS | bar: 2021-02-08 to 2021-03-15
Staffing | bar: 2021-02-08 to 2021-03-15
Plan and Confirm organizational hierarchy and structure |  | AEC | AEC | bar: 2021-02-08 to 2021-02-22
Determine profiles for who needs to be hired (skills, experience, # of people) |  | AEC | AEC | bar: 2021-02-08 to 2021-03-15
Create job descriptions |  | AEC | AEC | bar: 2021-02-08 to 2021-03-15
Recruit |  | AEC | AEC | bar: 2021-03-01 to 2021-03-15
Create job postings |  | AEC | AEC | bar: 2021-03-01 to 2021-03-15
Post jobs |  | AEC | AEC | bar: 2021-03-01 to 2021-03-15
Interview and complete reference checks |  | AEC | AEC | bar: 2021-03-01 to 2021-03-15
Write offer/hiring agreements |  | AEC | AEC | bar: 2021-03-01 to 2021-03-15
Hire Staff |  | AEC | AEC
Order Uniforms |  | Client
Determine HR polices & create HR Manual |  | AEC | AEC
Areas needed for hiring agreements |  | AEC | AEC
Areas not immediately needed for hiring agreements |  | AEC | AEC
Marketing | bar: 2021-02-08 to 2021-03-15
Design and order Logo/business cards/stationary |  | D and S | D and S | bar: 2021-02-08 to 2021-03-15
Create marketing plan (pre-opening through end of Year 1) |  | AEC | AEC | AEC | Bobby/Rich | 2021-02-08: AEC; 2021-02-15: Bobby/Rich; 2021-02-22: Bobby/Rich; 2021-03-01: Bobby/Rich
Pre-Opening Campaign
Determine promotion/pre-sale pricing |  | AEC | bar: 2021-02-08 to 2021-03-08
Determine media to use |  | AEC | bar: 2021-02-08 to 2021-03-08
Traditional: Direct mail, newspaper, coupons |  | AEC | AEC | bar: 2021-02-08 to 2021-03-08
Signage preopening and after opening |  | Client | Client | bar: 2021-02-08 to 2021-03-08
Develop Website (early part of pre-opening process) |  | Team | Team | bar: 2021-02-08 to 2021-03-15
Social media, blogging, facebook etc |  | Team | Team | bar: 2021-03-08 to 2021-03-15
Marketing plan for after opening |  | AEC | AEC
Determine promotions |  | AEC | AEC
Determine media to use |  | AEC | AEC | bar: 2021-02-08 to 2021-03-01
Traditional: Direct mail, newspaper, coupons |  | AEC | AEC | bar: 2021-02-08 to 2021-03-01
Internet |  | AEC | AEC | bar: 2021-02-08 to 2021-03-01
Website |  | AEC | AEC | bar: 2021-02-08 to 2021-03-01
Social networking |  | AEC | AEC | bar: 2021-02-08 to 2021-03-01
Create/Print membership, trial and service information/pricing collatoral materials (see forms) |  | AEC | AEC | bar: 2021-02-08 to 2021-03-01
Order membership scan key tags |  | AEC | AEC | bar: 2021-02-08 to 2021-03-01
Sales | bar: 2021-02-08 to 2021-03-15
Create and print forms/collatoral material - see form sections |  | Team | Team
Develop Sales Systems & Processes |  | AEC | AEC
Weekly sales meetings/action plans |  | AEC | AEC
Goals |  | AEC | AEC
Daily, monthly, weekly action plan |  | AEC | AEC
Community outreach (businesses/organizations to contact, partnerships, events) |  | AEC | AEC
Prospect follow-up |  | AEC | AEC
Sales trackingand reporting system (computerized system and reporting forms). This is also seen in the recommended reports sheet |  | AEC
Memberships sold |  | AEC | AEC
Daily, Weekly, Monthly, Yearly, and by sales person/compared to goals |  | AEC | AEC
Ancillary services by package type |  | AEC | AEC
Inquiries |  | AEC | AEC
Appointments set/showed |  | AEC | AEC
Tours |  | AEC | AEC
Conversion rates (Closing %) |  | AEC | AEC
Marketing Sources |  | AEC | AEC
Members locations by zip code/other member location analysis
Train sales team |  | AEC | bar: 2021-03-08 to 2021-03-15
Managing and closing prospects |  | AEC | AEC | bar: 2021-03-08 to 2021-03-15
Greeting - Needs Assessment - Services/Programs - Tour - Close - Follow-up |  | AEC | AEC | bar: 2021-03-08 to 2021-03-15
Emphasis on points of differentiation |  | AEC | AEC | bar: 2021-03-08 to 2021-03-15
Managing the phone inquiry |  | AEC | AEC | bar: 2021-03-08 to 2021-03-15
Managing the tour |  | AEC | AEC | bar: 2021-03-08 to 2021-03-15
How to overcome objections |  | AEC | AEC | bar: 2021-03-08 to 2021-03-15
Must ask questions |  | AEC | AEC | bar: 2021-03-08 to 2021-03-15
Email communication |  | AEC | AEC | bar: 2021-03-08 to 2021-03-15
Form completion |  | AEC | AEC | bar: 2021-03-08 to 2021-03-15
Using lead tracking and prospect database/Sales Tracking Form |  | AEC | AEC | bar: 2021-03-08 to 2021-03-15
Operations | bar: 2021-02-08 to 2021-03-15
Manager on Duty Training | bar: 2021-02-15 to 2021-03-15
Determine technology needs and order |  | AEC | AEC | bar: 2021-02-15 to 2021-03-15
Hardware: computers, printers, scanners, front desk camera, fax |  | AEC | AEC | bar: 2021-02-15 to 2021-03-15
Microsoft office suite |  | AEC | AEC | bar: 2021-02-15 to 2021-03-15
Club management software (prospect/sales management, member database, reports) | bar: 2021-02-15 to 2021-03-15
Financial management (i.e. quickbooks) | bar: 2021-02-15 to 2021-03-15
Credit card processing set up | bar: 2021-02-15 to 2021-03-15
Monthly member billing setup | bar: 2021-02-15 to 2021-03-15
Choose and install alarm system | bar: 2021-03-01 to 2021-03-15
Choose and install phone system | bar: 2021-03-01 to 2021-03-15
Choose and install music/TV system | bar: 2021-03-01 to 2021-03-15
Set up utilities | bar: 2021-03-01 to 2021-03-15
Determine facility cleaning needs and hire company/staff | bar: 2021-03-01 to 2021-03-15
Order cleaning and maintenance supplies | bar: 2021-03-01 to 2021-03-15
Order office supplies | bar: 2021-03-01 to 2021-03-15
Order uniforms | bar: 2021-03-01 to 2021-03-15
Order Name Tags | bar: 2021-03-01 to 2021-03-15
Develop scheduling procedures
Use of scheduling software
Appointment confirmation system
Cancellation policies and procedures
Develop Emergency Procedures | bar: 2021-02-15 to 2021-03-15
CPR, first aid, theft, evacuation and power outages | bar: 2021-02-15 to 2021-03-15
Create incident report and procedures | bar: 2021-02-15 to 2021-03-15
Front Desk - develop policies & procedures, forms, Create Manual | bar: 2021-02-15 to 2021-03-15
Front Desk Systems Training | bar: 2021-02-15 to 2021-03-15
General Information (address, phone numbers, website, directions, hours) | bar: 2021-02-15 to 2021-03-15
Uniforms and Name Tags | bar: 2021-02-15 to 2021-03-15
Answering the phone/transferring calls/taking messages | bar: 2021-02-15 to 2021-03-15
Greeting prospects and prospect inquiries | bar: 2021-02-15 to 2021-03-15
Greeting members and checking them in | bar: 2021-02-15 to 2021-03-15
Guest policies, procedures and fees | bar: 2021-02-15 to 2021-03-15
Cancellation and freeze requests | bar: 2021-02-15 to 2021-03-15
Member complaints | bar: 2021-02-15 to 2021-03-15
Emergencies | bar: 2021-02-15 to 2021-03-15
Point of Sale system | bar: 2021-02-15 to 2021-03-15
Towels | bar: 2021-02-15 to 2021-03-15
Opening and Closing procedures | bar: 2021-02-15 to 2021-03-15
Working the TV and music systems | bar: 2021-02-15 to 2021-03-15
Appointment scheduling, confirmation, and cancellations | bar: 2021-02-15 to 2021-03-15
Issuing new or replacement scan cards/key tags | bar: 2021-02-15 to 2021-03-15
Selling gift certificates | bar: 2021-02-15 to 2021-03-15
Important names and contact information | bar: 2021-02-15 to 2021-03-15
Staff | bar: 2021-02-15 to 2021-03-15
R & M and utility vendors | bar: 2021-02-15 to 2021-03-15
Landlord/property manager
Pricing Information
Insurance - Noted above Phase One | bar: 2021-02-08 to 2021-03-15
Obtain Relevant Insurance -liability insurance, property, workers compensation, other | bar: 2021-02-15 to 2021-03-15
Repairs and Maintenance | bar: 2021-02-08 to 2021-03-15
Equipment Maintenance
Label all equipment with numbers
Track mileage and usage of cardio machines
Choose repair and maintenance vendor
Develop cleaning schedule
Develop system for repairing equipment (what notice goes on machine, who calls in repairs, who follows-up with vendor
Forms & Collatoral Material | bar: 2021-02-08 to 2021-03-15
Sales & Marketing | bar: 2021-02-15 to 2021-03-15
Membership Agreement | bar: 2021-02-15 to 2021-03-15
Guest sign-in sheet | bar: 2021-02-15 to 2021-03-15
Client Service Agreements (Personal Training, Group Training, Massage etc) | bar: 2021-02-15 to 2021-03-15
Pricing Sheet | bar: 2021-02-15 to 2021-03-15
Program and service brochures/flyers | bar: 2021-02-15 to 2021-03-15
Trial membership cards | bar: 2021-02-15 to 2021-03-15
Member Information (hrs of operation, policies) | bar: 2021-02-15 to 2021-03-15
Member Updates | bar: 2021-02-15 to 2021-03-15
Cancellation form | bar: 2021-02-15 to 2021-03-15
Freeze form | bar: 2021-02-15 to 2021-03-15
Member account change/update form (address, contact, billing info) | bar: 2021-02-15 to 2021-03-15
Front Desk | bar: 2021-02-15 to 2021-03-15
Front desk check list (opening,change of shift, closing) | bar: 2021-02-15 to 2021-03-15
Register reconciliation | bar: 2021-02-15 to 2021-03-15
Appointment reminder cards | bar: 2021-02-15 to 2021-03-15
Fitness | bar: 2021-02-15 to 2021-03-15
Fitness Sales and team training | bar: 2021-02-15 to 2021-03-15
Fitness evaluation process | bar: 2021-02-15 to 2021-03-15
Health History (PARQ) | bar: 2021-02-15 to 2021-03-15
Workout cards | bar: 2021-02-15 to 2021-03-15
Personal training log | bar: 2021-02-15 to 2021-03-15
Emergencies | bar: 2021-02-15 to 2021-03-15
Incident report | bar: 2021-02-15 to 2021-03-15
Financial Management (see recommended reports sheet for more detail) | bar: 2021-02-08 to 2021-03-15
Daily Bookkeeping - input receipts, prepare bank deposit | bar: 2021-02-15 to 2021-03-15
Accounts Receivable | bar: 2021-02-15 to 2021-03-15
Create billing process | bar: 2021-02-15 to 2021-03-15
Create bad debt follow-up process | bar: 2021-02-15 to 2021-03-15
Accounts Payable
Create process for inputting, approving, and generating bill payment
Payroll - choose payroll company and develop systems for tracking hours/pay | bar: 2021-02-15 to 2021-03-15
Monthly Reporting | bar: 2021-02-15 to 2021-03-15
Cash report | bar: 2021-02-15 to 2021-03-15
Balance sheet | bar: 2021-02-15 to 2021-03-15
Goals vs. actuals | bar: 2021-02-15 to 2021-03-15
Bad debts | bar: 2021-02-15 to 2021-03-15
Reproject financial speadsheets going forward | bar: 2021-02-15 to 2021-03-15
Goal Setting and Reporting - see reports sheet | bar: 2021-02-08 to 2021-03-15